## WorkHub Plan
ID | Area | Item / Question | Type | Priority | Status | Owner | Decision needed / Notes
W01 | WorkHub | Clock in/out — real hours + 30-min break deduction | Bug fix | P0 | VERIFIED LIVE | Coder | Core off-paper capability. Watched it work.
W02 | WorkHub | Leave requests save real dates (no 'Unknown Date') | Bug fix | P1 | VERIFIED LIVE | Coder | Old crash + Unknown-Date both fixed.
W03 | WorkHub | Nav cleaned: no Schedule tab / Team Dir / Wiki / dup My-Schedule | Bug fix | P2 | VERIFIED LIVE | Coder | As SuperAdmin; full gating needs Andrei.
W04 | WorkHub | Sign-out -> /login (+ clears cache) | Bug fix | P1 | CODE-VERIFIED | Coder | Was dumping into CoralOS ('/'). Confirm live.
W05 | WorkHub | My Profile -> /workhub/profile (not HR module) | Bug fix | P1 | CODE-VERIFIED | Coder | Confirm the profile page is a worker profile.
W06 | Roles | Gating recognizes 'crew' + hides projects/team/wiki/docs for workforce | Bug fix | P0 | CODE-VERIFIED | Coder | Needs live confirm AS Andrei.
W07 | WorkHub | Manual late-entry submit persists (submitLateEntry) | Verify | P1 | CODE-REAL / UNCONFIRMED | Florin | Action exists, old error gone; toolbar blocked live click. Click once to confirm 'submitted for approval'.
W08 | WorkHub | Site-visit structured fields render + save | Verify | P1 | UNVERIFIED | Planner/Florin | Toolbar blocked the form. db-site-visits target exists.
W09 | WorkHub | Site-visit -> quote seeding (populate quote header) | Build | P2 | NOT STARTED | Coder | SITE-VISIT-TO-QUOTE. Client/address/contact/scope -> quote header.
W10 | Perf | WORKHUB-INP: ~2.2s interaction freeze | Bug + Decision | P1 | OPEN | Coder | Lead theory: worker app hydrates all 16 ERP DBs. DECISION: scope worker app off the global store (recommended) vs optimize serializer. Also audit capture-phase scroll listeners.
W11 | WorkHub | Geofence on shift clock-in (CLOCK-GEOFENCE) | Build | P2 | NOT STARTED | Coder | Project-location field now exists (LocationColumn). Radius per project; off-site -> pending lane.
W12 | WorkHub | Approval review UI (foreman/owner approves pending entries) | Verify + Build | P1 | PARTIAL | Coder | hrApprovalRequest is created (pending). Confirm/Build the review+approve queue scoped by role.
W13 | WorkHub | 'Clocked In' badge stale on My Schedule after clock-out | Bug (minor UI) | P2 | OPEN | Coder | Badge doesn't clear post clock-out.
W14 | WorkHub | Header shows 'User' briefly before name resolves | Bug (minor) | P3 | OPEN | Coder | Load flash; cosmetic.
R01 | Roles | Coder hard-coded '¦¦ crew' acceptance instead of migrating data | Decision | P1 | OPEN | Florin | DECISION: migrate crew->TENANT_ENTERPRISE_WORKFORCE in DB + drop the special-case (single source of truth), OR keep the hack. Recommend migrate.
R02 | Roles | Make role editable in Team settings (badge is display-only text) | Build | P1 | NOT STARTED | Coder | You can only set module-access + password, not the role. No UI path to change role.
R03 | Roles | Role auto-applies its access-profile defaults | Build | P2 | PARTIAL | Coder | ROLE_ACCESS_DEFAULTS exist; make selecting 'Workforce' auto-apply so no manual per-user toggling.
R04 | Roles | Role picker/invite must only ever write canonical ROLES | Build | P1 | OPEN | Coder | This whole morning traced to a stored role ('crew') the code never knew.
D01 | Deploy | Promote develop -> main (production/app.coral-group.be is behind) | Action | P0 | BLOCKING | Florin | Andrei/workers see OLD code until promoted. All fixes are develop-only.
D02 | Process | Vercel preview toolbar hijacks clicks/comments during E2E | Process | P2 | OPEN | Florin | Disable v0/comment mode on the preview for clean testing.
D03 | Process | Textarea synthetic-typing flakiness during automation | Verify | P3 | OPEN | Planner | Likely automation artifact, not a real-user bug — confirm.
D04 | Milestone | Tag 'ground zero' after Tier-1 verified on staging | Milestone | P1 | PENDING | Florin | Promote develop->staging->main->tag once hours+gating confirmed.
P01 | Portal | PORTAL-WELCOME-PLACEHOLDER ('{name}' + 'Portal.tracking' raw strings) | Bug | P2 | QUEUED | Coder | Interpolate client name; translate the key.
P02 | Tasks | TASKS-I18N-NAMES (sidebar shows raw 'Tasks.sidebar.*' keys) | Bug | P2 | QUEUED | Coder | Untranslated i18n keys.
P03 | Cockpit | COCKPIT data-first roadmap (rollups->hours->CPI->change-orders->milestones->gantt->safety) | Build | P2 | POST-BASELINE | Coder | Data-first: each card only when its data is real.
P04 | Grid | GRID-REPLACE (DataSheetGrid -> TanStack, parked) | Build | P3 | PARKED | Coder | Post-ground-zero.
A01 | Assistant | CORAL-ASSISTANT (layered AI assistant, paid tier) | Build + Decision | P2 | SPECCED | Florin/Coder | Full layered spec in coral-assistant.md. DECISION: when to start. Read-only slice first. DPA (L7) is Florin's.
AC01 | Accountant | In-app read-only Peppol-invoices view (ACCOUNTANT role): PDF, UBL, Peppol status, per invoice | Build | P1 | NOT STARTED | Coder | Path A base. ACCOUNTANT role exists (read-only financials, no seat cost). Tenant-scoped.
AC02 | Accountant | Bulk export by period -> ZIP of UBL+PDF + CSV index | Build | P1 | NOT STARTED | Coder | For import into accounting software. Tenant-scoped, rate-limited, audited.
AC03 | Accountant | Export format decision | Decision | P1 | OPEN | Florin | Which accounting software does the accountant use? Raw UBL is universal; some need a specific import layout.
AC04 | Accountant | Auto-deliver copy to accountant on Peppol send (Path B) | Build | P2 | NOT STARTED | Coder | Idempotent, failure-tolerant, never blocks the client send.
AC05 | Accountant | Delivery channel decision (Path B) | Decision | P2 | OPEN | Florin | Peppol to accountant's access point (if they have a Peppol ID) vs email UBL+PDF.
AC06 | Accountant | Audit log + instant revoke of accountant access/delivery | Build | P1 | NOT STARTED | Coder | Every view/download/export/delivery logged; revoke kills access + auto-delivery.
AC07 | Accountant | Confirm accountant engagement/mandate covers data processing | Action | P1 | OPEN | Florin | Florin corrected: not a new DPA. B2C client invoices ARE personal data (name/home address/work done) so it's not 'all public' — but sharing with your own accountant is routine and usually covered by their existing engagement letter. Just confirm it.
DASH01 | Data layer | CoralOS read-only MCP connector -> live dashboard + assistant read access | Build + Decision | P1 | OPEN | Coder/Florin | No external services connected (0). Best data is CoralOS. A read-only CoralOS connector powers BOTH a live Cowork dashboard AND the assistant's L1 data layer — one build, two payoffs. DECISION: build the connector vs keep the dashboard inside CoralOS (/admin/dashboard already exists).
W15 | WorkHub / Invites | SMS gateway for mobile worker invites (text the WorkHub login link) | Decision + Build | P2 | SPECCED | Florin / Coder | WORKHUB-INVITE-MOBILE part 2. QR-code + copy-link path works NOW with no provider. SMS to the invitee's phone needs a gateway — Twilio / MessageBird / Sinch (cost + env keys). Stays specced until we implement.